## Tracking
TRACKING UVM VERIFICATION - CONFIGUABLE AXI APB BRIDGE
| STT | Hạng mục | Nội dung | Ngày cập nhật | Vấn đề | Định hướng / Hành động | Hoàn thành | NOTE
RTL | 1 | AXI FIFO | Nghiên cứu FIFO phù hợp | 2026-03-05 | Nên chọn Async hay Sync FIFO | Chọn Async FIFO và tìm hiểu về AsyncFifo | Done
|  |  | Nghiên cứu về Asynchonus FIFO | 2026-03-12 |  |  | Done
|  |  | Thiết kế RTL khối ASFIFO | 2026-03-18 |  |  | Done | Đã hoàn thành ASYNC FIFO
| 2 | RW_SELECT | Nghiên cứu chi tiết khối | 2026-03-04 |  |  | Done
|  |  | Thiết kế khối RW_SELECT | 2026-03-21 |  |  | Done | Đã hoàn thành RW_SELECT
| 3 | ADDR_DECODER | Nghiên cứu cách giải mã địa chỉ theo FIX, INCR, WRAP | 2026-03-05 |  |  | Done
|  |  | Thiết kế khối ADDR_DECODER | 2026-03-22 | Cần giải quyết việc chuyển đổi burst (INCR, WRAP) của AXI thành các transaction đơn lẻ phù hợp với APB. |  | Done
|  |  | Hoàn thiện khối ADDR_DECODER | 2026-03-22 |  |  | Done | Đã hoàn thành ADDR_DECODER
| 4 | APB_REGISTER | Nghiên cứu cách thanh ghi lưu trữ data | 2026-03-18 |  |  | Done
|  |  | Nghiên cứu về register map address | 2026-03-23 | Cách chuyển các biến địa chỉ Slave bên trong Register ra cho APB MASTER | Nối thẳng trực tiếp các biến đó luôn, không sử dụng parameter nữa | Done
|  |  | Hoàn thiện khối APB_REGISTER | 2026-03-26 |  |  | Done | Đã hoàn thành APB_REGISTER
| 5 | APB Master | Nghiên cứu cách giải mã địa chỉ theo FIX, INCR, WRAP | 2026-03-18 | Chưa rõ flow FIFO → APB master |  | Done
|  |  | Hoàn thiện khối APB_Master | 2026-03-28 |  |  | Done | Đã hoàn thành APB_MASTER
| 6 | AXI APB Bridge (Top) | Hoàn thiện RTL | 2026-03-30 |  |  | Done | Đã hoàn thành RTL
TB | 7 | Lý thuyết UVM, system verilog |  | 2026-03-01 |  |  | Done
|  | Xây dựng SDK kiến trúc Uvm_test_top |  | 2026-03-20 |  |  | Done
|  | Xây dựng Vplan và verify RTL đơn giản để check 1 số trạng thái |  | 2026-04-01 |  |  | Done | Hoàn thành vplan
|  | Build apb master vip |  | 2026-04-14 | transaction => if => config => drv => mon => sequencer => agent => package |  | Done | Hoàn thành apb_master_vip
|  | Build apb slave vip |  | 2026-04-14 | transaction => if => config => drv => mon => sequencer => agent => package |  | Done | Hoàn thành apb_slave_vip
|  | Build axi vip |  | 2026-04-14 | transaction => if => config => drv => mon => sequencer => agent => package |  | Done | Hoàn thành axi_vip
|  | Build Testbench |  | 2026-04-28 | tb => env => basetest => sequence => scoreboard => package |  | Done
|  | Hoàn thành UVM |  | 2026-05-15 | test hết tất cả testcase |  | Done
|  | Functional Coverage |  | 2026-05-23 |  |  | Done

## Spec APB REGISTER
Table 2-1. APB Slave 0, 1,2 Base/Size Register (BAMSn)
|  | Address | Abbreviation | Register name
|  | 0x00 | BAMS0 | Base Address & Memory Size 0
|  | 0x04 | BAMS1 | Base Address & Memory Size 1
|  | 0x08 | BAMS2 | Base Address & Memory Size 2
|  | 0x0C | BIR | Bridge Interrupt Register
|  | Others | Reserved
Table 2-2. Base Address & Memory Size 0 (BAMS0)
Bit | Name | Type | Default Value | Description
[31:10] | Base | RW | 22'h00 | Base address of bits[31:10]
[9:2] | - | Rsvd | 0 | Reserved
[1:0] | Size | RW | 2'b10 | Size of address space
KB select by Unit signal
00: 1kb <0000_0000 => 0000_03FF>
01: 2kb <0000_0000 => 0000_07FF>
10: 4kb <0000_0000 => 0000_0FFF>
11: 8kb <0000_0000 => 0000_1FFF>
Table 2-3. Base Address & Memory Size 1 (BAMS1)
Bit | Name | Type | Default Value | Description
[31:10] | Base | RW | {3'h000;10'h4} | Base address of bits[31:10]
[9:2] | - | Rsvd | 0 | Reserved
[1:0] | Size | RW | 2'b10 | Size of address space
KB select by Unit signal
00: 1kb <0000_0000 => 0000_03FF>
01: 2kb <0000_0000 => 0000_07FF>
10: 4kb <0000_0000 => 0000_0FFF>
11: 8kb <0000_0000 => 0000_1FFF>
Table 2-4. Base Address & Memory Size 2 (BAMS2)
Bit | Name | Type | Default Value | Description
[31:10] | Base | RW | 22'h00008 | Base address of bits[31:10]
[9:2] | - | Rsvd | 0 | Reserved
[1:0] | Size | RW | 2'b10 | Size of address space
KB select by Unit signal
00: 1kb <0000_0000 => 0000_03FF>
01: 2kb <0000_0000 => 0000_07FF>
10: 4kb <0000_0000 => 0000_0FFF>
11: 8kb <0000_0000 => 0000_1FFF>
Table 2-5. Bridge Interrupt Register (BIR)
Bit | Name | Type | Default Value | Description
[31:2] | - | Rsvd | 0 | Reserved
1 | DecErrSt | RW1C | 0 | Interrupt status. DecErrSt is set when receiving a non-existing address. or an address that matches multiple slaves
0: This interrupt has occurred.
1: Writing a '1' to clears this interrupt.
0 | DecErrEn | RW | 1 | Enable or disable DecErrIntr
0: Disable
1: Enable

## Vplan
Total Items | 60
Pass Items | 60
Fail Items | 0
NY Items | 0
Section | Main Title | Description | Testname | Priorite | Method | Owner | Status | Milestone Remark | Founded Bug
A. | APB REGISTER CONFIG
1 | Register check
1.1 | Read Default Value Test | 1. Wait for clock and reset 2. Read default value for register; BAMS0 , BAMS1 , BAMS2 & BIR | tc11_read_default | HIGH | directed | Nhân Đoàn | PASS | 2026-04-16 | phát hiện lỗi ở giá trị mặc định thanh ghi BIR
1.2 | Read Write Reserved region Test | 1. Wait for clock and reset 2. Write and read reserved region register from address 0x14 - 0xFF => Data read matching value 32'h0000_0000 | tc12_read_write_reserved | HIGH | directed | Nhân Đoàn | PASS | 2026-04-16 |  | tc
1.3 | Read Write Register BAMS Access | 1. Wait for clock and reset. 2. Automatically fetch all BAMS registers from the RAL model. 3. Perform 20 randomized write/read cycles for each register. 4. Use UVM RAL Mirroring (UVM_CHECK) for automatic comparison. 5. Expected Outcome: - Read data matches Mirrored value. - Reserved bits are automatically masked and read as 0. | tc13_bams_read_write_access | HIGH | directed | Nhân Đoàn | PASS | 2026-04-16 | phát hiện lỗi rw bit [1:0] thanh ghi BAMS1
1.4 | Read Write Register BIR Access | 1. Wait for clock and reset. 2. Perform a Clear-on-Start by writing 0x2 to BIR[1] (DecErrSt). 3. Execute randomized write/read cycles specifically for BIR register. 4. Use RAL Mirror (UVM_CHECK) to verify W1C and RW field logic. 5. Expected Outcome: - Writing '1' to bit [1] clears the bit. - Writing to Reserved bits [31:2] has no effect (read as 0). - Field DecErrEn [0] behaves as a standard RW bit. | tc14_bir_read_write_access | HIGH | directed | Nhân Đoàn | PASS | 2026-04-16
1.5 | Byte Access Test for BAMS Register | 1. Wait for clock and reset. 2. Automatically fetch all BAMS registers from the RAL model. 3. Perform 20 randomized write/read cycles for each register. 4. Use UVM RAL Mirroring (UVM_CHECK) for automatic comparison. 5. Expected Outcome: - Read data matches Mirrored value. - Reserved bits are automatically masked and read as 0." | tc15_bams_byte_access | HIGH | directed | Nhân Đoàn | PASS | 2026-04-16
B. | AXI WRITE TRANSACTION
2 | FIXED Burst
2.1 | Write to Slave 0 | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b00; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd1; | tc21_psel0_fixed_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08 | phát hiện lỗi bresp không phản hồi
2.2 | Write to Slave 1 | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b00; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd1; | tc22_psel1_fixed_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
2.3 | Write to Slave 2 | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b00; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd1; | tc23_psel2_fixed_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
2.4 | Write to Slave 1 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b00; AWSIZE=3'b010; AWLEN=3'd0~3'd1; PSLVERR = 1 | tc24_psel0_fixed_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
2.5 | Write to Slave 2 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b00; AWSIZE=3'b010; AWLEN=3'd0~3'd1; PSLVERR = 1 | tc25_psel1_fixed_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
2.6 | Write to Slave 3 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b00; AWSIZE=3'b010; AWLEN=3'd0~3'd1; PSLVERR = 1 | tc26_psel2_fixed_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
2.7 | Random write transaction | AWADDR=$urandom(); AWBURST=2'b00; AWSIZE=$urandom(); AWLEN=$urandom(); | tc27_pselx_fixed_wr_random | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
3 | INCR Burst
3.1 | Write to Slave 0 | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b01; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd7; | tc31_psel0_incr_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
3.2 | Write to Slave 1 | AWADDR=$urandom_range(32'h1000,32'h1FFF); AWBURST=2'b01; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd7; | tc32_psel1_incr_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
3.3 | Write to Slave 2 | AWADDR=$urandom_range(32'h2000,32'h2FFF); AWBURST=2'b01; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd7; | tc33_psel2_incr_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
3.4 | Write to Slave 0 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b01; AWSIZE=3'b010; AWLEN=3'd7; | tc34_psel0_incr_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
3.5 | Write to Slave 1 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h1000,32'h1FFF); AWBURST=2'b01; AWSIZE=3'b010; AWLEN=3'd7; | tc35_psel1_incr_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
3.6 | Write to Slave 2 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h2000,32'h2FFF); AWBURST=2'b01; AWSIZE=3'b010; AWLEN=3'd7; | tc36_psel2_incr_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
3.7 | Write to Slave 0 & 1 - 4 byte crossing | AWADDR=$urandom_range(32'h0FE7,32'h0FF0); AWBURST=2'b01; AWSIZE=3'b010; AWLEN=3'd7; | tc37_psel01_incr_wr_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
3.8 | Write to Slave 1 & 2 - 4 byte crossing | AWADDR=$urandom_range(32'h1FE7,32'h1FF0); AWBURST=2'b01; AWSIZE=3'b010; AWLEN=3'd7; | tc38_psel12_incr_wr_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
3.9 | Random write transaction | AWADDR=$urandom(); AWBURST=2'b01; AWSIZE=$urandom(); AWLEN=$urandom(); | tc39_pselx_incr_wr_random | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
4 | WRAP Burst
4.1 | Write to Slave 0 | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b10; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd7; | tc41_psel0_wrap_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
4.2 | Write to Slave 1 | AWADDR=$urandom_range(32'h1000,32'h1FFF); AWBURST=2'b10; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd7; | tc42_psel1_wrap_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
4.3 | Write to Slave 2 | AWADDR=$urandom_range(32'h2000,32'h2FFF); AWBURST=2'b10; AWSIZE=3'd0 ~ 3'd2; AWLEN=3'd0~3'd7; | tc43_psel2_wrap_wr | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
4.4 | Write to Slave 1 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h0000,32'h0FFF); AWBURST=2'b10; AWSIZE=3'b010; AWLEN=3'd7; | tc44_psel0_wrap_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
4.5 | Write to Slave 2 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h1000,32'h1FFF); AWBURST=2'b10; AWSIZE=3'b010; AWLEN=3'd7; | tc45_psel1_wrap_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
4.6 | Write to Slave 3 - 4 byte - slave have PSLVERR | AWADDR=$urandom_range(32'h2000,32'h2FFF); AWBURST=2'b10; AWSIZE=3'b010; AWLEN=3'd7; | tc46_psel2_wrap_wr_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
4.7 | Write to Slave 0 & 1 - 4 byte wrap crossing | AWADDR=$urandom_range(32'h0FE7,32'h0FF0); AWBURST=2'b10; AWSIZE=3'b010; AWLEN=3'd7; | tc47_psel01_wrap_wr_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
4.8 | Write to Slave 1 & 2 - 4 byte wrap crossing | AWADDR=$urandom_range(32'h1FE7,32'h1FF0); AWBURST=2'b10; AWSIZE=3'b010; AWLEN=3'd7; | tc48_psel12_wrap_wr_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
4.9 | Random write transaction | AWADDR=$urandom(); AWBURST=2'b10; AWSIZE=$urandom(); AWLEN=$urandom(); | tc49_pselx_wrap_wr_random | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
C. | AXI READ TRANSACTION
5 | FIXED Burst
5.1 | Read to Slave 0 | ARADDR=$urandom_range(32'h0000,32'h0FFF); ARBURST=2'b00; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd1; | tc51_psel0_fixed_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
5.2 | Read to Slave 1 | ARADDR=$urandom_range(32'h1000,32'h1FFF); ARBURST=2'b00; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd1; | tc52_psel1_fixed_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
5.3 | Read to Slave 2 | ARADDR=$urandom_range(32'h2000,32'h2FFF); ARBURST=2'b00; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd1; | tc53_psel2_fixed_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
5.4 | Read to Slave 1 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h4000,32'h4FFF); ARBURST=2'b00; ARSIZE=3'b010; ARLEN=3'd0~3'd1; | tc54_psel0_fixed_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
5.5 | Read to Slave 2 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h1001,32'h1FFF); ARBURST=2'b00; ARSIZE=3'b010; ARLEN=3'd0~3'd1; | tc55_psel1_fixed_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
5.6 | Read to Slave 3 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h2000,32'h2FFF); ARBURST=2'b00; ARSIZE=3'b010; ARLEN=3'd0~3'd1; | tc56_psel2_fixed_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
5.7 | Random read transaction | ARADDR=$urandom(); ARBURST=2'b00; ARSIZE=$urandom(); ARLEN=$urandom(); | tc57_pselx_fixed_rd_random | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
6 | INCR Burst
6.1 | Read to Slave 0 | ARADDR=$urandom_range(32'h0000,32'h0FFF); ARBURST=2'b01; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd7; | tc61_psel0_incr_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
6.2 | Read to Slave 1 | ARADDR=$urandom_range(32'h1000,32'h1FFF); ARBURST=2'b01; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd7; | tc62_psel1_incr_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
6.3 | Read to Slave 2 | ARADDR=$urandom_range(32'h2000,32'h2FFF); ARBURST=2'b01; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd7; | tc63_psel2_incr_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
6.4 | Read to Slave 1 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h0000,32'h0FFF); ARBURST=2'b01; ARSIZE=3'b010; ARLEN=3'd7; | tc64_psel0_incr_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
6.5 | Read to Slave 2 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h1000,32'h1FFF); ARBURST=2'b01; ARSIZE=3'b010; ARLEN=3'd7; | tc65_psel1_incr_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
6.6 | Read to Slave 3 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h2000,32'h2FFF); ARBURST=2'b01; ARSIZE=3'b010; ARLEN=3'd7; | tc66_pse2_incr_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
6.7 | Read from Slave 0 & 1 - 4 byte crossing | ARADDR=$urandom_range(32'h0FE7,32'h0FF0); ARBURST=2'b01; ARSIZE=3'b010; ARLEN=3'd7; | tc67_psel01_incr_rd_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
6.8 | Read from Slave 1 & 2 - 4 byte crossing | ARADDR=$urandom_range(32'h1FE7,32'h1FF0); ARBURST=2'b01; ARSIZE=3'b010; ARLEN=3'd7; | tc68_psel12_incr_rd_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
6.9 | Random read transaction | ARADDR=$urandom(); ARBURST=2'b01; ARSIZE=$urandom(); ARLEN=$urandom(); | tc69_pselx_incr_rd_random | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
7 | WRAP Burst
7.1 | Read to Slave 0 | ARADDR=$urandom_range(32'h0000,32'h0FFF); ARBURST=2'b10; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd7; | tc71_psel0_wrap_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
7.2 | Read to Slave 1 | ARADDR=$urandom_range(32'h1000,32'h1FFF); ARBURST=2'b10; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd7; | tc72_psel1_wrap_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
7.3 | Read to Slave 2 | ARADDR=$urandom_range(32'h2000,32'h2FFF); ARBURST=2'b10; ARSIZE=3'd0 ~ 3'd2; ARLEN=3'd0~3'd7; | tc73_psel2_wrap_rd | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
7.4 | Read to Slave 1 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h0000,32'h0FFF); ARBURST=2'b10; ARSIZE=3'b010; ARLEN=3'd7; | tc74_psel0_wrap_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
7.5 | Read to Slave 2 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h1000,32'h1FFF); ARBURST=2'b10; ARSIZE=3'b010; ARLEN=3'd7; | tc75_psel1_wrap_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
7.6 | Read to Slave 3 - 4 byte - slave have PSLVERR | ARADDR=$urandom_range(32'h2000,32'h2FFF); ARBURST=2'b10; ARSIZE=3'b010; ARLEN=3'd7; | tc76_psel2_wrap_rd_err | HIGH | directed | Nhân Đoàn | PASS | 2026-05-09
7.7 | Read from Slave 0 & 1 - 4 byte crossing | ARADDR=$urandom_range(32'h0FE7,32'h0FF0); ARBURST=2'b10; ARSIZE=3'b010; ARLEN=3'd7; | tc77_psel01_wrap_rd_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
7.8 | Read from Slave 1 & 2 - 4 byte crossing | ARADDR=$urandom_range(32'h1FE7,32'h1FF0); ARBURST=2'b10; ARSIZE=3'b010; ARLEN=3'd7; | tc78_psel12_wrap_rd_cross | HIGH | directed | Nhân Đoàn | PASS | 2026-05-08
7.9 | Random read transaction | ARADDR=$urandom(); ARBURST=2'b10; ARSIZE=$urandom(); ARLEN=$urandom(); | tc79_pselx_wrap_rd_random | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
D. | AXI READ WRITE RANDOM TRANSACTION
8 | RANDOM ALL
8.1 | Random transaction - random addr, burst, size, data, error | AWADDR=$urandom(); AWBURST=$urandom(); AWSIZE=$urandom(); AWLEN=$urandom(); ARADDR=$urandom(); ARBURST=$urandom(); ARSIZE=$urandom(); ARLEN=$urandom(); | tc81_wr_rd_random_test | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-09
E. | INTERRUPT
9 | interrupt triggle and clear
9.01 | Trigger interrupt | 1. Wait for clock and reset 2. Enable DecErrEn (write BIR[0]=1) 3. Access invalid address 4. Check DecErrSt = 1 and interrupt asserted => Interrupt must be triggered | tc91_enable_decerr_interrupt | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
9.02 | Disable interrupt | 1. Wait for clock and reset 2. Disable DecErrEn (write BIR[0]=0) 3. Access invalid address 4. Check DecErrSt = 1 and interrupt not asserted => Interrupt must be disabled | tc92_disable_decerr_interrupt | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
9.03 | Clear interrupt (RW1C) | 1. Enable DecErrEn (write BIR[0]=1) 2. Trigger DECERR (invalid address) 3. Check DecErrSt = 1 4. Write BIR[1]=1 (RW1C) 5. Read back → DecErrSt must be 0 => Interrupt must be cleared correctly | tc93_clear_decerr_interrupt | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
9.04 | Sticky interrupt behavior | 1. Enable DecErrEn (write BIR[0]=1) 2. Trigger DECERR multiple times 3. Check DecErrSt remains 1 4. Do not clear → value must stay 1 => Interrupt must be sticky until cleared | tc94_sticky_decerr_interrupt | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
F. | APB ADDRESS REMAP TEST
10 | DYNAMIC ADDRESS REMAP
10.1 | Basic Slave Address Remap | 1. Wait for clock and reset 2. Write new base address to BAMS0/BAMS1/BAMS2 3. Generate AXI read/write transaction to new region 4. Check correct PSEL assertion => New address mapping must work correctly | tc101_dynamic_remap_basic | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
10.2 | Old Address Region Invalid | 1. Remap slave address region 2. Access old address region 3. Check DECERR response => Old address region must become invalid after remap | tc102_old_region_invalid | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
10.3 | Runtime Address Remap During Traffic | 1. Start AXI traffic 2. Change BAMS register during active transaction 3. Continue traffic 4. Check no deadlock or wrong decode => Runtime remap must operate correctly | tc103_runtime_remap | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-15
10.4 | Random Address Remap Stress | 1. Randomize BAMS registers 2. Generate random AXI read/write traffic 3. Check PSEL and DECERR behavior => Decoder must remain stable under stress | tc104_random_remap_stress | HIGH | randomize | Nhân Đoàn | PASS | 2026-05-15
10.5 | Burst Crossing After Remap | 1. Configure new slave regions 2. Generate INCR/WRAP burst crossing boundary 3. Check correct slave decode => Crossing burst after remap must work correctly | tc105_burst_cross_after_remap | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15
10.6 | Reserved Region After Remap | 1. Configure limited slave regions 2. Access reserved address area 3. Check DECERR response => Reserved region must always return decode error | tc106_reserved_region_after_remap | HIGH | directed | Nhân Đoàn | PASS | 2026-05-15

## Vplan without UVM (hidden)
Total Items
Pass Items
Fail Items
NY Items
Section | Main Title | Description | Testname | Pass Conditon | Method | Owner | Status | Milestone | Remark
1 | Check APB Register
1.1 | Initial value of register BAMS0–3, BIR | 1. Reset hệ thống 2. Read tất cả register tại addr: 0x00, 0x04, 0x08, 0x0C, 0x10 | 11_init_reg | BIR=0x0BAMS0 = 32'h0000_0002 BAMS1 = 32'h0000_1002 BAMS2 = 32'h0000_2002 BAMS3 = 32'h0000_3002 BIR = 32'h0000_0000
1.2 | Reserved Access | 1: Write paddr_reg = 8'h99, pwdata_reg = 32'hDEAD_BEEF → read 2: Write paddr_reg = 8'hFC, pwdata_reg = 32'h1234_5678 → read 3: Write paddr_reg = 8'hA1, pwdata_reg = 32'hAAAA_AAAA → read | 12_reserved_access_reg | prdata_reg = 32'h0000_0000 (mọi case)
1.3 | Read Write | 1: Write paddr_reg = 8'h00, pwdata_reg = 32'h0000_5001 → read 2: Write paddr_reg = 8'h04, pwdata_reg = 32'h0000_6002 → read 3: Write paddr_reg = 8'h08, pwdata_reg = 32'h0000_7003 → read 4: Write paddr_reg = 8'h0C, pwdata_reg = 32'h0000_8000 → read 5: Write paddr_reg = 8'h10, pwdata_reg = 32'hFFFF_FFFF → read 6: Write paddr_reg = 8'h10, pwdata_reg = 32'h0000_0000 → read | 13_read_write_reg | 1: prdata_reg = 32'h0000_5001 2: prdata_reg = 32'h0000_6002 3: prdata_reg = 32'h0000_7003 4: prdata_reg = 32'h0000_8000 5: prdata_reg[0x10]=32'h0000_0001 6: prdata_reg[0x10]=32'h0000_0000
2 | Check AXI to APB trans
2.1 | FIXED burst | 1: AWADDR=0x0000_0000, AWBURST=FIXED, AWLEN=3 2: Write 4 beat data 3: Quan sát APB signal khi write 4: ARADDR=0x0000_0000, AWBURST=FIXED, AWLEN=3 5: Quan sát APB signal khi read | 21_axi_fixed
2.2 | INCR burst | 1: AWADDR=0x0000_0000, AWBURST=INCR, AWLEN=3 2: Write 4 beat data 3: Quan sát APB signal khi write 4: ARADDR=0x0000_0000, AWBURST=INCR, AWLEN=3 5: Quan sát APB signal khi read | 22_axi_incr
2.3 | WRAP burst | 1: AWADDR=0x0000_0000, AWBURST=WRAP, AWLEN=3 2: Write 4 beat data 3: Quan sát APB signal khi write 4: ARADDR=0x0000_0000, AWBURST=WRAP, AWLEN=3 5: Quan sát APB signal khi read | 23_axi_wrap
2.4 | BYTE ACCESS (WSTRB → PSTRB) | 1: AWADDR=0x0000_0000, AWBURST=INCR, AWLEN=3, WSTRB = 2: Write 4 beat data 3: Quan sát APB signal 4: ARADDR=0x0000_0000, AWBURST=FIXED, AWLEN=3 5: AWADDR=0x0000_0000, AWBURST=WRAP, AWLEN=3, WSTRB = 0 6: Write 4 beat data 7: Quan sát APB signal 8: ARADDR=0x0000_0000, AWBURST=FIXED, AWLEN=3 | 24_axi_strb
3 | Check Interrupt
3.1 | Interrupt assert then clear | 1: AWADDR=32'h5000_0000 → write 2: ARADDR=32'h5000_0000 → read | 31_axi_intr | Không có PSEL assert BRESP=DECERR RRESP=DECERR DecErrInt sẽ bật
|  | 3: Write BIR = 32'h0000_0002 (RW1C) |  | DecErrIntr = 0

## BUG REPORT
BUG REPORT 1: SAI GIÁ TRỊ MẶC ĐỊNH THANH GHI BIR
Theo spec thì thanh ghi BIR (0xC) có giá trị mặc định là 0x01
Nhưng scoreboard và dạng sóng ghi nhận khi đọc giá trị mặc định của thanh ghi BIR (0xC) là 0x00
Sau khi reset, khi pwrite = 0 (ở chế độ đọc), và đồng thời penable và pready bằng 0 thì ghi nhận giá trị thanh ghi BIR (0xC) prdata = 0x0.
Truy code RTL thì thấy lỗi ở dòng 153 file APB_REGISTER, lỗi gán giá trị mặc định bit DecErrEn <= 0
Cần sửa lại giá trị mặc định bit DecErrEn <= 1.
BUG REPORT 2: Không thể write vào bit [1:0] thanh ghi BAMS1 (0X04)
Theo spec thì bit [1:0] của thanh ghi BAMS1 (0X04) có thể RW.
Nhưng scoreboard khi nhận kết quả không thể write vào bit [1:0] của BAMS1 (0X04), thanh ghi luôn giữ giá trị mặc định 2 bit [1:0] là 0x2
Dạng sóng cũng ghi nhận tại thanh ghi BAMS1 (0x04) khi write 2 bit 00 vào bit[1:0] thì khi đọc lại vẫn giữ giá trị 10 (0x2), và khi write 2 bit 11 vào bit[1:0] thì khi đọc vẫn giữ giá trị 10 (0x2)
Truy code RTL thì thấy lỗi dòng 106 file APB Register, lỗi khi gán paddr_reg == BAMS2_ADDR. Cần sửa lại paddr_reg == BAMS1_ADDR
BUG REPORT 3: BRESP bên phía AXI DOMAIN không phản hồi
bug xảy ra khi viết tc24_psel0_fixed_wr_err
Khi phía APB Master nhận được PSLVERR nhưng BRESP lại hoàn toàn không có phản hồi gì => đây là bug RTL
Tracing code thì ta thấy bị lệch timing nên chỉ cần điều chỉnh lại TIming là BRESP sẽ hoạt động bình thường
Code trước khi sửa: do bresp_in chưa đồng bộ được vì bresp_in đang lên cùng lúc với PSLVERR => cần phải delay đồng bộ qua phía axi domain
Code sau khi sửa:
BUG REPORT 4: Lỗi AXI Read Handshake gây sai RLAST và mismatch dữ liệu
Trong quá trình kiểm tra giao dịch đọc của AXI-to-APB Bridge, log mô phỏng báo lỗi giá trị kênh R thay đổi khi RVALID=1 và RREADY=0.
Đồng thời, scoreboard cũng báo mismatch giữa dữ liệu expected và actual.
Lỗi xuất hiện trong trường hợp RVALID và RREADY cùng được giữ ở mức 1 trong nhiều hơn một chu kỳ clock. Khi đó, mỗi chu kỳ có RVALID && RREADY đều được xem là một read beat hợp lệ theo AXI protocol.
Tuy nhiên, dữ liệu RDATA hoặc tín hiệu RLAST không được cập nhật/capture đúng theo từng beat, dẫn đến việc monitor hoặc scoreboard ghi nhận sai transaction.
Cần sửa lại file AXI_CLOCK_DOMAIN.sv